# UNDP Social and Environmental Standards:

# Stakeholder Engagement Plan

Please refer to the UNDP Social and Environmental Standards Toolkit for additional information.

Appropriately scaled plans. No one type or format of a stakeholder engagement plan will accommodate all projects. Its content will depend on various factors, including the nature, scale, location, and duration of project; the diverse interests of stakeholders; the scale of the project’s potential positive and adverse impacts on people and the environment; and the likelihood of grievances.

For a relatively small project with few if any potential adverse social and environmental impacts or initial stakeholder concerns (e.g. Low Risk project, straightforward Moderate Risk project), it is likely that only a “simplified” stakeholder engagement plan would be needed, focusing primarily on initial consultations, information disclosure and periodic reporting (see Box 8). In such cases, the “plan” would be relatively simple and easily described in the body of the Project Document (that is, no separate plan would be needed).

Box 8. Triggering the appropriate scale of stakeholder engagement plans

- Simplified stakeholder engagement plan: Project funding aimed at providing technical support (training in survey equipment) and materials (office space, computers, GPS equipment) to a national land and survey commission will likely have minimal impact on stakeholders other than the government.

- Comprehensive stakeholder engagement plan: Project funding to the same land and survey commission to actually conduct land titling in indigenous and forest-dependent communities across the nation, however, would require a comprehensive plan.

A project with greater complexity and potentially significant adverse social and environmental impacts (complex Moderate Risk project or High Risk project) should elaborate a more strategic plan. A “comprehensive” plan would outline mechanisms that buttress not just disclosure and good communications, but iterative consultations and possibly consent processes over the course of the social and environmental assessment process, development of mitigation and management plans, monitoring project implementation, and evaluation. A separate, detailed stakeholder engagement plan should be appended to the Project Document (see outline below).

All stakeholder engagement plans – whether simplified or comprehensive (see below) – should address basic minimum criteria. The following checklist (Table 7) will help ensure that the plan addresses key issues and components.

| Table 7. Key questions for developing a stakeholder engagement plan |  |
| --- | --- |
| Who | - Which stakeholder groups and individuals are to be engaged based on the stakeholder analysis? - Have potentially marginalized groups and individuals been identified among stakeholders? |
| Why | - Why is each stakeholder group participating (e.g. key stakeholder objectives and interests)? |
| What | - What is the breadth and depth of stakeholder engagement at each stage of the project cycle? - What decisions need to be made through stakeholder engagement? |
| How | - How will stakeholders be engaged (strategy and methods, including communications)? - Are special measures required to ensure inclusive participation of marginalized or disadvantaged groups? |
| When | - What is the timeline for engagement activities, and how will they be sequenced, including information disclosure? |
| Responsibilities | - How have roles and responsibilities for conducting stakeholder engagement been distributed among project partners (e.g. resident mission, executing agency, consultants, NGOs)? - What role will stakeholder representatives play? - Are stakeholder engagement facilitators required? |
| Resources | - What will the stakeholder engagement plan cost and under what budget? |

Building mutual trust and ensuring meaningful and effective engagement is facilitated by stakeholder ownership of the relevant processes. All efforts should be made to work with the relevant stakeholders to design by mutual agreement the engagement and consultation processes, including mechanisms for inclusiveness, respecting cultural sensitivities, and any required consent processes. Cultural understanding and awareness is central to meaningful stakeholder engagement.

Moreover, a general solicitation of feedback or input cannot be relied upon, nor accepted as the sole method of consultation. Information laden questions presenting various options, the reasons for those options, and their consequences may be a better method in that it presents information in a relationship-building manner, does not assume full stakeholder knowledge of the project plans, and solicits input on specific project instances instead of placing the impetus on the stakeholder to make seemingly high-level suggestions.

Recall that stakeholder engagement may be minimal at certain times and intense at others, depending on the issues and particular project phase. Also, targeted input from select stakeholder groups may be needed at key points in project development and implementation.

As project information changes – perhaps from subsequent risk assessments, the addition of project activities, stakeholder concerns – the stakeholder engagement plan should be reviewed and modified accordingly to ensure its effectiveness in securing meaningful and effect stakeholder participation.

The stakeholder engagement plan should also anticipate if/when professional, neutral facilitators might be needed to lead key engagement activities. For projects where the stakeholder engagement process is likely to be complex or sensitive, social advisors or other expert staff should help design and facilitate the process and assist with participatory methodologies and other specialized techniques.

Grievance redress processes for the project need to be described in the stakeholder engagement plan. Section 3.4 above elaborates on relevant SES requirements.

The plan should also outline a reasonable budget for stakeholder engagement activities, including potential support for groups to facilitate their participation where necessary (noting that meeting locations should be as convenient as possible and stakeholder acceptance of such support should not be interpreted as endorsement of the project).

Table 8 below provides a rough outline for a simplified stakeholder engagement plan. Many approaches exist, and this is one example of outlining key elements. It is important to not simply list stakeholders and say they will be consulted, but to identify why they are being engaged, how engagement will proceed, who will do it, when, and how it will be financed/supported.

| Table 8. Rough template of simplified stakeholder engagement plan |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stakeholder Group | Why included (interests) | Participation methods |  | Timeline | Cost est. |
|  |  | Method | Responsibility |  |  |

Below is an example of elements that should be addressed in a comprehensive stakeholder engagement plan. The scope and level of detail of the plan should be scaled to fit the needs of the project.

Outline of a Comprehensive Stakeholder Engagement Plan

1. Introduction

- Briefly describe the project including design elements and potential social and environmental issues. Where relevant, include maps of the project site and surrounding area.

2. Regulations and Requirements

- Summarize any legal, regulatory, donor/lender requirements pertaining to stakeholder engagement applicable to the project. This may involve public consultation and disclosure requirements related to the social and environmental assessment process as well as relevant international obligations.

3. Summary of any previous stakeholder engagement activities

- If any stakeholder engagement activities had been undertaken to date, including information disclosure and/or consultation, provide the following details:

- Type of information disclosed, in what forms and languages (e.g., oral, brochure, reports, posters, radio, etc.), and how it was disseminated

- Locations and dates of any meetings undertaken to date

- Individuals, groups, and/or organizations that have been consulted

- Key issues discussed and key concerns raised

- Responses to issues raised, including any commitments or follow-up actions

- Process undertaken for documenting these activities and reporting back to stakeholders

4. Project Stakeholders

- List the key stakeholder groups who will be informed about and engaged in the project (based on stakeholder analysis). These should include persons or groups who:

- Are directly and/or indirectly affected by the project

- Have “interests” in the project that determine them as stakeholders

- Have the potential to influence project outcomes or operations

- [Examples of potential  stakeholders are beneficiaries and project-affected communities, local organizations, NGOs, and government authorities, indigenous peoples; stakeholders can also include politicians, private sector companies, labor unions, academics, religious groups, national environmental and social public sector agencies, and the media]

- Consider capacities of various stakeholder groups to effectively participate in the stakeholder engagement activities, and include measures to support them where capacity is limited

5. Stakeholder Engagement Program

- Summarize the purpose and goals of the stakeholder engagement program

- Briefly describe what information will be disclosed, in what formats and languages, and the types of methods that will be used to communicate this information to each of the stakeholder groups identified in section 4 above. Methods used may vary according to target audience, for example:

  - Newspapers, posters, radio, television

  - Information centers and exhibitions or other visual displays

  - Brochures, leaflets, posters, non-technical summary documents and reports

- Briefly describe the methods that will be used to engage and/or consult with each of the stakeholder groups identified in section 4. Methods used may vary according to target audience, for example:

  - Interviews with stakeholder representatives and key informants

  - Surveys, polls, and questionnaires

  - Public meetings, workshops, and/or focus groups with specific groups

  - Participatory methods

  - Other traditional mechanisms for consultation and decision-making

- Describe how the views of women and other relevant groups (e.g. minorities, elderly, youth, other marginalized groups) will be taken into account and their participation facilitated

- Where relevant, define activities that require prior consultation and FPIC from indigenous peoples (and refer to Indigenous Peoples Plan and FPIC protocols)

- Outline methods to receive feedback and to ensure ongoing communications with stakeholders (outside of a formal consultation meeting)

- Describe any other engagement activities that will be undertaken, including participatory processes, joint decision-making, and/or partnerships undertaken with local communities, NGOs, or other project stakeholders. Examples include benefit-sharing programs, stakeholder-led initiatives, and training and capacity building/support programs.

6. Timetable

- Provide a schedule outlining dates/periodicity and locations where various stakeholder engagement activities, including consultation, disclosure, and partnerships will take place and the date by which such activities will be undertaken

7. Resources and Responsibilities

- Indicate who will be responsible for carrying out the specified stakeholder engagement activities

- Specify the budget and other resources allocated toward these activities

- [For projects with significant potential impacts and multiple stakeholder groups, it is advisable to hire a qualified stakeholder engagement facilitator to undertake all or portions of the stakeholder engagement activities]

8. Grievance Mechanism

- Describe the process by which people concerned with or potentially affected by the project can express their grievances for consideration and redress. Who will receive grievances, how and by whom will they be resolved, and how will the response be communicated back to the complainant? (see Guidance Note on Grievance Redress Mechanisms)

- Ensure reference is made to and stakeholders are informed of the availability of UNDP’s Accountability Mechanism (Stakeholder Response Mechanism, SRM, and Social and Environmental Compliance Unit, SECU) as additional avenues of grievance redress.

9. Monitoring and Reporting

- Describe any plans to involve project stakeholders (including target beneficiaries and project-affected groups) or third-party monitors in the monitoring of project implementation, potential impacts and management/mitigation measures

- Describe how and when the results of stakeholder engagement activities will be reported back to project-affected and broader stakeholder groups. Examples include newsletters/bulletins, social and environmental assessment reports; monitoring reports.

As modified, see Asian Development Bank (ADB), Strengthening Participation, p. 43.

Practical Approaches to Ensuring the Full and Effective Participation of Indigenous Peoples in ReDD+ (September 2013), BMZ, FPCP, UN-ReDD, p.12.

IFC Stakeholder Engagement, p. 101.

Outline relies on content provided in IFC, Guidance Note 1: Assessment and Management of Environmental and Social Risks and Impacts (2012), Annex B.